## Milestones
Reanalysis → manuscript
Target: manuscript ready 23 Dec 2026 • final proof 30 Dec • emergency buffer 31 Dec.
Milestone | Deadline | Required outcome | Blocks through | Checklist done
M1 Sources and design ready | 2026-10-14 | Audited source register, documented outlet criteria and eligibility protocol | 2 | 0%
M2 Pilot validated for scaling | 2026-10-30 | Working codebook and prompt, separate assessment, documented scale/no-scale decision | 5 | 0%
M3 Corpus extraction complete | 2026-11-12 | Traceable outputs, failure register and targeted source review | 7 | 0%
M4 Coding and interpretations settled | 2026-11-26 | Final coding, configuration memos and comparative evidence | 9 | 0%
M5 Results complete | 2026-12-04 | Reproducible summaries, checked sensitivity analyses and results draft | 11 | 0%
M6 Complete manuscript draft | 2026-12-15 | Revised methods, discussion and conclusion integrated with frozen intro/lit | 13 | 0%
M7 Publication package ready | 2026-12-23 | Verified claims, references, quotations, tables and repository materials | 15 | 0%
Final deadline | 2026-12-30 | Final proof and manuscript frozen; 31 December is emergency buffer only | 16 | 0%
Progress counts completed checklist items cumulatively; it does not replace the completion conditions or validation gates.
Planning windows are calendar days, not estimates of full-time effort. No automatic task extension.

## Work blocks
Bounded work blocks
2026 • Japan time • 2–3 calendar days per block; gaps remain free for other projects.
Block | Work block | Start | Deadline | Deliverable | Checklist done | Actual completion | Deliverable / version | Unresolved issue | Next bounded action | Milestone impact | Completion condition
1 | Source audit | 2026-10-05 | 2026-10-07 | frozen source register and source-quality report. | 0% | [5 empty] | Done when every source has a unique ID and a recorded quality status; unresolved retrieval cases have an explicit disposition.
2 | Eligibility and outlet protocol | 2026-10-12 | 2026-10-14 | protocol v1 and supported outlet mapping. Completes M1. | 0% | [5 empty] | Done when eligibility and classification decisions can be applied without relying on anticipated results.
3 | Human-led pilot | 2026-10-19 | 2026-10-21 | pilot source interpretations, provisional codebook and extraction prompt. | 0% | [5 empty] | Done when the pilot yields a usable extraction specification and explicit coding decisions.
4 | Calibration | 2026-10-26 | 2026-10-28 | working prompt/codebook and calibration report. | 0% | [5 empty] | Done when remaining errors are characterised and the working procedure is ready for separate assessment.
5 | Separate assessment | 2026-10-29 | 2026-10-30 | assessment report and scale/no-scale decision. Completes M2 if passed. | 0% | [5 empty] | Done when the decision is supported by the predeclared criteria. Failure uses the next block for repair, not premature full-corpus processing.
6 | Corpus processing, batch A | 2026-11-03 | 2026-11-05 | processed first batch and monitoring log. | 0% | [5 empty] | Done when the planned batch has outputs or recorded failures and monitoring supports continuation.
7 | Corpus processing, batch B and reconciliation | 2026-11-10 | 2026-11-12 | complete extraction register and reviewed exception queue. Completes M3. | 0% | [5 empty] | Done when every source has a final eligibility/output status and consequential extraction problems have been addressed.
8 | Final coding consistency | 2026-11-17 | 2026-11-19 | analytical dataset and final codebook. | 0% | [5 empty] | Done when the dataset matches the final definitions and is ready for descriptive analysis.
9 | Reconstruction and comparative close reading | 2026-11-24 | 2026-11-26 | configuration memos and SIPC comparison matrix. Completes M4. | 0% | [5 empty] | Done when each retained configuration has an inspectable argument and counterevidence has been considered. If key interpretations remain unresolved, use the contingency block rather than inventing closure.
10 | Numerical summaries and sensitivity | 2026-12-01 | 2026-12-02 | reproducible tables and comparison checks. | 0% | [5 empty] | Done when headline quantities and comparative claims are checked and limitations recorded.
11 | Results and evidence | 2026-12-03 | 2026-12-04 | results draft with tables and quotation register. Completes M5. | 0% | [5 empty] | Done when every principal result has a traceable numerical or textual basis.
12 | Contingency or external review | 2026-12-08 | 2026-12-10 | resolved blocker list or reviewed results draft. | 0% | [5 empty] | This block is reserved capacity, not permission to extend previous tasks indefinitely.
13 | Complete manuscript | 2026-12-13 | 2026-12-15 | complete manuscript draft. Completes M6. | 0% | [5 empty] | Done when all sections form a complete argument and no substantive placeholder is concealed.
14 | Claim and publication audit | 2026-12-18 | 2026-12-20 | corrected manuscript and verified evidence package. | 0% | [5 empty] | Done when the manuscript and supporting materials agree.
15 | Package and freeze | 2026-12-22 | 2026-12-23 | manuscript ready for submission or sharing. Completes M7. | 0%
16 | Final buffer | 2026-12-29 | 2026-12-30 | final proof and deadline confirmation. | 0% | [5 empty] | 31 December is reserved for an emergency correction, not new analysis. Submission, public repository publication and other external releases remain separate actions requiring the author's instruction.

## Checklist
Reanalysis checklist
Edit yellow cells. “Done” counts toward block and milestone progress.
Task ID | Block | Work block | Action | Status | Completed on | Notes
1.1 | 1 | Source audit | Preserve the previous analytical files and record their versions. | Not started
1.2 | 1 | Source audit | Identify the broadest available source pool; do not inherit the 917-record eligibility boundary automatically. | Not started
1.3 | 1 | Source audit | Verify IDs, metadata, URLs and source-text linkage. | Not started
1.4 | 1 | Source audit | Check exact/near duplicates, empty texts, truncation and obvious extraction artefacts. | Not started
1.5 | 1 | Source audit | Repair retrievable problem texts and record unresolved cases without overwriting originals. | Not started
1.6 | 1 | Source audit | Assign stable source locations and text hashes for evidence checking. | Not started
2.1 | 2 | Eligibility and outlet protocol | Specify the six SIPC dimensions and analytical fields. | Not started
2.2 | 2 | Eligibility and outlet protocol | Define explicit, indirect and absent educational AI futures, including present applications and uncertain cases. | Not started
2.3 | 2 | Eligibility and outlet protocol | Specify retention of multiple visions and conflicting speakers. | Not started
2.4 | 2 | Eligibility and outlet protocol | Define domestic, foreign and transnational coverage labels. | Not started
2.5 | 2 | Eligibility and outlet protocol | Document outlet-selection rationale and institutional evidence for grouping; revise labels where necessary. | Not started
2.6 | 2 | Eligibility and outlet protocol | Keep outlet-group labels out of extraction prompts. | Not started
2.7 | 2 | Eligibility and outlet protocol | Record collection information that can be recovered and list historical details that remain unavailable. | Not started
3.1 | 3 | Human-led pilot | Select a varied pilot across outlets, periods, technologies and educational contexts. | Not started
3.2 | 3 | Human-led pilot | Record and justify pilot size; expand only for a specific unresolved distinction. | Not started
3.3 | 3 | Human-led pilot | Read full texts and identify separate visions with supporting passages. | Not started
3.4 | 3 | Human-led pilot | Develop categories within SIPC fields, with boundaries and examples. | Not started
3.5 | 3 | Human-led pilot | Record ambiguities and initial interpretive memos without imposing the old five configurations. | Not started
3.6 | 3 | Human-led pilot | Specify machine-readable outputs linking visions, speakers, evaluations, actions and exact evidence. | Not started
4.1 | 4 | Calibration | Record model/version, settings, dates and prompt versions. | Not started
4.2 | 4 | Calibration | Compare pilot outputs against full-text interpretations. | Not started
4.3 | 4 | Calibration | Check omitted visions, attribution, negation, modality and unsupported inference. | Not started
4.4 | 4 | Calibration | Test automatic quotation matching and output validation. | Not started
4.5 | 4 | Calibration | Correct recurring problems and retest affected cases. | Not started
4.6 | 4 | Calibration | Set assessment criteria before viewing the separate assessment outputs. | Not started
5.1 | 5 | Separate assessment | Select articles not used for calibration, covering relevant corpus variation. | Not started
5.2 | 5 | Separate assessment | Document sample size, selection and reviewer arrangements. | Not started
5.3 | 5 | Separate assessment | Assess eligibility, completeness, attribution and category accuracy against source texts. | Not started
5.4 | 5 | Separate assessment | Examine field-specific and systematic errors, not only aggregate agreement. | Not started
5.5 | 5 | Separate assessment | Report independent agreement only if independent ratings exist. | Not started
5.6 | 5 | Separate assessment | Decide whether to scale, revise/reassess, or simplify the extraction task. | Not started
6.1 | 6 | Corpus processing, batch A | Freeze the working prompt/codebook versions for this batch. | Not started
6.2 | 6 | Corpus processing, batch A | Process articles independently; record run details and save outputs. | Not started
6.3 | 6 | Corpus processing, batch A | Check identifiers, schema and exact evidence matches automatically. | Not started
6.4 | 6 | Corpus processing, batch A | Review flagged cases and source-check a spread of ordinary cases. | Not started
6.5 | 6 | Corpus processing, batch A | Record coverage, failures and any systematic problem. | Not started
7.1 | 7 | Corpus processing, batch B and reconciliation | Process remaining sources using the validated procedure. | Not started
7.2 | 7 | Corpus processing, batch B and reconciliation | Resolve extraction failures and uncertain eligibility decisions. | Not started
7.3 | 7 | Corpus processing, batch B and reconciliation | Review ambiguous, conflicting and flagged cases. | Not started
7.4 | 7 | Corpus processing, batch B and reconciliation | Apply consequential prompt/category revisions to affected earlier records. | Not started
7.5 | 7 | Corpus processing, batch B and reconciliation | Reconcile source counts, exclusions and retained article IDs. | Not started
8.1 | 8 | Final coding consistency | Consolidate category definitions and review affected records. | Not started
8.2 | 8 | Final coding consistency | Distinguish missing, unresolved and absent values. | Not started
8.3 | 8 | Final coding consistency | Check difficult boundaries such as literacy/talent, harm/prevention and restriction/adoption. | Not started
8.4 | 8 | Final coding consistency | Preserve multiple visions and their evidence links. | Not started
8.5 | 8 | Final coding consistency | Record coding coverage and outstanding limitations. | Not started
9.1 | 9 | Reconstruction and comparative close reading | Develop candidate imaginaries from the new material. | Not started
9.2 | 9 | Reconstruction and comparative close reading | Examine all six SIPC dimensions and explicit relationships. | Not started
9.3 | 9 | Reconstruction and comparative close reading | Retrieve supporting, contrasting and contradictory cases across relevant contexts and outlets. | Not started
9.4 | 9 | Reconstruction and comparative close reading | Record boundaries, overlaps, alternatives and unspecified elements. | Not started
9.5 | 9 | Reconstruction and comparative close reading | Document the scope of close reading and why further expansion was or was not needed. | Not started
9.6 | 9 | Reconstruction and comparative close reading | Compare with the old configurations only after developing the new interpretations. | Not started
10.1 | 10 | Numerical summaries and sensitivity | Calculate valid denominators and coding coverage. | Not started
10.2 | 10 | Numerical summaries and sensitivity | Summarise constituent dimensions without estimating imaginary membership. | Not started
10.3 | 10 | Numerical summaries and sensitivity | Compare outlet groups and inspect within-group concentration. | Not started
10.4 | 10 | Numerical summaries and sensitivity | Run yes-only and leave-one-outlet-out checks. | Not started
10.5 | 10 | Numerical summaries and sensitivity | Examine technology/geography/context composition where relevant to principal claims. | Not started
10.6 | 10 | Numerical summaries and sensitivity | Retain temporal checks only if needed and supported; keep sparse earlier coverage descriptive. | Not started
10.7 | 10 | Numerical summaries and sensitivity | Verify scripts reproduce the final outputs. | Not started
11.1 | 11 | Results and evidence | Answer RQ1 through reconstruction, RQ2 across SIPC and RQ3 through comparison. | Not started
11.2 | 11 | Results and evidence | Select quotations from the documented interpretive sample, including boundary cases. | Not started
11.3 | 11 | Results and evidence | Verify quotation context, attribution and translations. | Not started
11.4 | 11 | Results and evidence | Remove prevalence/dominance claims unsupported by the unit of coding. | Not started
11.5 | 11 | Results and evidence | Keep reported promises distinct from demonstrated educational effects. | Not started
12.1 | 12 | Contingency or external review | Address unfinished validation or reconstruction first. | Not started
12.2 | 12 | Contingency or external review | If no blockers remain, obtain feedback where available and check the RQ–evidence alignment. | Not started
12.3 | 12 | Contingency or external review | Record changes required; decline optional scope expansion. | Not started
13.1 | 13 | Complete manuscript | Update methods to the actual final process and resolve reporting placeholders. | Not started
13.2 | 13 | Complete manuscript | Revise discussion and conclusion around the final evidence. | Not started
13.3 | 13 | Complete manuscript | Keep intro/lit frozen except for factual corrections and essential alignment. | Not started
13.4 | 13 | Complete manuscript | Remove claims of methodological novelty not intended by the study. | Not started
13.5 | 13 | Complete manuscript | Check narrative consistency, repetition and word budget. | Not started
14.1 | 14 | Claim and publication audit | Check claims against tables, texts, memos and methodological references. | Not started
14.2 | 14 | Claim and publication audit | Verify citations, references, translations, figure labels and table denominators. | Not started
14.3 | 14 | Claim and publication audit | Confirm limitations reflect sampling, validation and classification. | Not started
14.4 | 14 | Claim and publication audit | Prepare repository materials and inspect copyright/access arrangements for source texts. | Not started
14.5 | 14 | Claim and publication audit | Test reproduction from the intended publication package. | Not started
15.1 | 15 | Package and freeze | Finalise repository link and materials description. | Not started
15.2 | 15 | Package and freeze | Apply target-journal formatting if a journal is selected. | Not started
15.3 | 15 | Package and freeze | Check abstract, keywords, statements and supplementary references. | Not started
15.4 | 15 | Package and freeze | Resolve critical issues; list any remaining optional refinements separately. | Not started
15.5 | 15 | Package and freeze | Freeze the manuscript, data and analysis versions. | Not started
16.1 | 16 | Final buffer | Resolve only consequential outstanding issues. | Not started
16.2 | 16 | Final buffer | Proofread the final manuscript and test all links. | Not started
16.3 | 16 | Final buffer | Confirm the final package is complete by 30 December. | Not started

## Working rules
Working rules and scope
Source: methods/reanalysis_checklist_and_deadlines.md • plan dated 4 October 2026.
Topic | Instruction
Scope | This plan retains the existing source collection and restarts analysis from full article texts. Intro and literature review remain frozen, apart from corrections required by the final evidence. Existing extractions, coding and configurations are preserved as the earlier analysis; they are not the reference standard for the new run.
How to update | Update task statuses and completion dates in Checklist. Record deliverable/version, blockers, next action and milestone impact in Work blocks. All yellow cells are editable.
Working rule | Each scheduled block lasts 2–3 calendar days. Reserve focused sessions within the block; a block does not assume full-time work every day.
Working rule | Dates between blocks are available for other projects. Do not fill them with optional analysis.
Working rule | Start each block with its stated deliverable and stop when the completion condition is met.
Working rule | At the end of an unfinished block, record the exact blocker and remaining work. Use a later contingency block or split the remainder into a bounded task; do not silently extend the deadline.
Working rule | Pilot and assessment are gates: do not scale processing while consequential extraction errors remain unresolved. If this delays a milestone, reduce optional analyses before weakening validation.
Working rule | Keep one protocol, versioned prompts and codebook, and a decision log. Revisit records affected by revisions rather than rerunning everything by default.
Working rule | Add analyses only if required by an RQ or a demonstrated validity problem. Extra models, topic modelling and causal temporal analysis are outside the default scope.
Working rule | Do not claim independent validation without independent ratings. Document the actual reviewer arrangement.
End-of-block record | For each block, record: actual completion date; deliverable/version; unresolved issue; next bounded action; effect on the next milestone. If behind schedule, prioritise source fidelity, validation and RQ evidence, and remove optional analyses first.
Final buffer | 31 December is reserved for emergency correction, not new analysis. External releases require the author’s instruction.